## Dashboard Page
[10 empty] | Date: 19/01/2016 | Comments Key
4+ Weeks Overdue
PM | Project | Stage 1 | Stage 2 Feasibility | Stage 3 Concept Design | Stage 4 Detailed Design | Stage 5 Delivery | Finance | Overall RAG | FacOps Action | Stakeholder Comments | 2-4 Weeks Overdue
Jerry Young | Albany House - Plant Optimisation | Board Date 01/03/2012 |  |  |  | Forecast Completion on 17-2-2017 170 day(s) late | Current Forecast Spend £300775 |  | YES | Change request was submitted to the board 26/11/2016 Extra information submitted specific meeting to discuss change request
Jerry Young | Baker Street Complex - Fire Compliance - Fire Alarms no MICC | Board Date 01/11/2012 |  |  |  | Forecast Completion on 30-4-2017 212 day(s) late | Current Forecast Spend £1506239 |  | YES | Change request was submitted to the board 26/11/2016 Extra information submitted specific meeting to discuss change request
John Murphy | Building Facades Risk Assessments (7 Building) | Board Date 20/08/2016 | Completed 2 day(s) late |  | Forecast Completion on 22-6-2017 on time |  | Current Forecast Spend £180000 |  |  | No Issue
John Murphy | 200 BPR Toilet Refurbishment | Board Date 28/11/2015 | Completed 334 day(s) late |  |  |  | Current Forecast Spend £419345 |  |  | Stage Gate 2: Was put on hold to redefine scope of works.
John Cousins | 172 BPR & Windsor House Chiller Remedial | Board Date 06/02/2014 |  |  |  | Forecast Completion on 20-3-2017 on time | Current Forecast Spend £1027000 |  |  | No Issue
John Cousins | Basement Leak Detection and Sump Pump | Board Date 15/10/2015 |  |  |  | Completed on time | Under budget by £17669 |  |  | Practical completion envisaged 12/12/2016
John Cousins | Toilet Flushing Upgrade | Board Date 15/10/2015 |  |  | Completed on time |  | Current Forecast Spend £409317 |  |  | Permission given to proceed to tender
John Murphy | Templar House Boiler Replacement | Board Date 14/08/2015 |  |  |  | Completed on time | Under budget by £0 |  |  | BMS to be address by FacOps
John Cousins | VSH Roof and Facades Repairs | Board Date 22/10/2015 |  |  | Forecast Completion on 15-5-2017 on time |  | Current Forecast Spend £571000 |  |  | Construction work to be started in 2017 financial year A variation to brief cost, and programme
Laurie Morely | 172 BPR LV Infrastructure Upgrade | Board Date 17/01/2016 |  |  | Completed 13 day(s) late |  | Current Forecast Spend £61226 |  |  | Tender Package to be sent out by 31st Janaury 2017.
John Murphy | 172 BPR 5th Floor Power | Board Date 20/08/2016 |  |  |  | Completed on time | Under budget by £0 |  |  | No Issue
Alan Crossan | 200 BPR New Kitchens 4th,5th and 6th Floors | Board Date 29/02/2016 |  |  |  | Completed 49 day(s) late | Under budget by £0 |  |  | PM to finalise costs
Laurie Morely | 13 Allsop Place Refurbishment ex-police cells to make new into lockers | Board Date 18/08/2016 |  |  |  | Completed 9 day(s) late | Under budget by £0 |  |  | PM to finalise costs
Laurie Morely | Uniform Store relocation to Penton Street | Board Date 29/09/2016 |  |  |  | Completed 3 day(s) early | Under budget by £0 |  |  | PM to finalise costs
Tony Hunter | LSTOC Accommodation Workstream | Board Date 01/02/2015 |  |  |  | Completed 104 day(s) early | Under budget by £168000 |  |  | Stage Gate 5 over due by 39 days
Martina Perkins | New Meeting Rooms for Steve Burton EOS Director | Board Date 18/05/2016 |  |  |  | Completed on time | Under budget by £59289 |  |  | No Issue
Martina Perkins | 2nd Floor Kitchen area Palestra | Board Date 25/08/2016 |  |  |  | Completed 23 day(s) early | Under budget by £0 |  |  | No Issue
Martin Smith | Templar House Basement Changeing Room for Chancery Lane Escalator Replacement Project | Board Date 01/02/2016 | [7 empty] | Stage gate 5 overdue by 239 days Issue a close out report noting the low quality drawings any new drawings will have to be a new project waiting on accounts payable to find out where final payment went
John Cousins | Griffith House Facade Repairs | Board Date 18/01/2017 |  |  |  |  | Current Forecast Spend £288000 |  |  | Stage Gate 1 date has now been missed. Project Manger to submit at the next board meeting 1st February 2017.
Helena Healy | Broadway PA/VA system | Completed 18/01/2017 |  |  |  | Forecast Completion on 4-4-2017 on time | Current Forecast Spend £84500 |  |  | Stage 1-4 has been approved.
Tony Hunter | 4L Emergancy Service Control Centre | Board Date 05/02/2017 |  |  |  |  | Current Forecast Spend £85368
Martina Perkins | Bringing Back to use Staircase/chained door leading to the track |  |  |  |  | Forecast Completion on 3-4-2017 on time | Current Forecast Spend £107100
Dashboard
Protect Sheet
Un-Protect Sheet
Add New Project
Archive Project
Update Project

## Tracker Sheet
Project Detail | [6 empty] | Stage Gate 1 |  |  | \ |  | Feasibility Stage Gate 2 | [10 empty] | Design Stage Gate 3 | [10 empty] | Design Stage Gate 4 | [10 empty] | Construction Stage Gate 5 | [10 empty] | Project Finance | [7 empty] | Project Comments |  | Status and Comments |  | Calculations
Projct ID | WBS Element | Project Name | Building | Project Manager | Facilities Operations | Project Sponsor | Project Requirement issued | Forecast Board Date | Actual Board Date |  | Rag Status | Baseline Start | Actual Start | Baseline Completion | Forecast Completion | Actual Completion | Stage Gate 2 Completion | Consultant | Actual Start | Forecast Completion | Actual Completion | RAG Status | Baseline Start | Actual Start | Baseline Completion | Forecast Completion | Actual Completion | Stage Gate 3 Completion | Designer | Actual Start | Forecast Completion | Actual Completion | RAG Status | Baseline Start | Actual Start | Baseline Completion | Forecast Completion | Actual Completion | Stage Gate 4 Completion | Designer | Actual Start | Forecast Completion | Actual Completion | RAG Status | Baseline Start | Actual Start | Baseline Completion | Forecast Completion | Contractual Practical Completion | Stage Gate 5 Completion | Contractor | Actual Start | Forecast Completion | Actual Completion | RAG Status | Approved Budget | EFC Forecast | YTD | Initial Budget | Outturn Cost |  |  | RAG Status | Risk & Issues: | Current Comments | Project Overall RAG Status | Stakeholder Comments | Stage Gate 2 Status | Overrun? | Stage Gate 3 Status | Overrun? | Stage Gate 4 Status | Overrun? | Stage Gate 5 Status | Overrun? | Finance | Stage Gate 5
PCP/12/033 | RX04F.014.2007.708.02 | Albany House - Plant Optimisation | Albany House | Jerry Young | Dave Parr | Simona Kuhl | 2012-01-30 | 2012-03-01 |  | Board Date 01/03/2012 | R | [33 empty] | 2015-03-10 | 2015-03-17 | 2016-08-31 | 2017-02-17 |  |  | BTU | G | R |  | R | 300775 | 300775 | 53779 | 89500 |  | 0% | -82.12% | G | Risks: (1) There has been discovery of asbestos, (2) Works will be undertaken in an occupied areas Issues (1) Poor contractor performance | Budget (+-): Change Request 06 has been issued and signed off Programme: Water systems works complete, balancing and commissioning has been completed by BTU, BTU are undertaking a number of critical valve replacements due to commence early October. The Air System commissioning report has been issued and actions have been undertaken. Logi-tek have completed their comissioning works. The IS team have requested some BMS functionality, CR06 has been signed to undertake these work, Logi-tek to undertake the works. Logi-tek have been appointed to undertake the outstadning comissioning as signed CR04 and 05. Programme and change request to be updated upon receipt of BTU information. | R | Change request was submitted to the board 26/11/2016 Extra information submitted specific meeting to discuss change request | [6 empty] | Forecast Completion on 17-2-2017 170 day(s) late |  | Current Forecast Spend £300775 | Stage Gate 5
PCP/15/006 | RX04F.014.2007.903.03 | Baker Street Complex - Fire Compliance - Fire Alarms no MICC | Baker Street, 210-212 (NW1) | Jerry Young | Dave Parr | Simona Kuhl | 2012-10-01 | 2012-11-01 |  | Board Date 01/11/2012 | R | [33 empty] | 2015-07-08 | 2015-07-08 | 2016-09-30 | 2017-04-30 |  |  | BBC | G | R |  | R | 1506239 | 1506239 | 379574 | 1107958 |  | 0% | -74.8% | G |  |  | R | Change request was submitted to the board 26/11/2016 Extra information submitted specific meeting to discuss change request | [6 empty] | Forecast Completion on 30-4-2017 212 day(s) late |  | Current Forecast Spend £1506239 | Stage Gate 5
PCP/16/020 | RX04F.033.307.01 | Building Facades Risk Assessments (7 Building) | Multi Sites | John Murphy | Robert Sciberras | Simona Kuhl | 2016-07-20 | 2016-08-20 |  | Board Date 20/08/2016 | R | 2016-05-01 | 2016-05-01 | 2016-10-26 | 2016-10-28 | 2016-10-28 | 2016-10-26 | M Hollis | G | G | G | G | [6 empty] | Vinci Technology |  |  |  |  | 2017-01-04 | 2017-01-04 | 2017-06-22 | 2017-06-22 |  |  |  | G | G |  | G | [11 empty] | 180000 | 180000 | 7500 | 180000 |  | 0% | -95.83% | G | Risk: Risk relating to appointment of Principal Designer may compromise progress. Issues: No Issues | Budget (+-): 20/01/17 Forecast remains unalterred although PD appointment in progress, CAR value to Survying Contractor lower than SG1 forecast and risk allowance to be re-evaluated. Programme: 20/01/17 Contract has been signed with a commencement date of 04/01/17and Baseline start date for SG4on site is 21/01/17 this may need CRF to be submitted. | G | No Issue | Completed | 2 day(s) late |  |  | Forecast Completion on 22-6-2017 on time |  |  |  | Current Forecast Spend £180000 | Stage Gate 4
PCP/16/007 | RX04F.033.303.02 | 200 BPR Toilet Refurbishment | 200 Buckingham Palace Road | John Murphy | Hakeem Makanju | Simona Kuhl | 2015-10-28 | 2015-11-28 |  | Board Date 28/11/2015 | R | 2015-09-28 | 2015-10-06 | 2015-11-08 | 2016-10-07 | 2016-10-07 |  | CBRE | R | R | R | R | [33 empty] | 419345 | 419345 | 17500 | 419345 |  | 0% | -95.83% | G | CBRE have completed all surveys. Update to be sent to project team. Report to follow. | Budget (+-): 20/01/17 Budget to be reviewed after receipt of quote following review of scope meeting held on 09/01/17. Programme: 20/01/17 Programme to be reviewed and revised following agreement of scope to be delivered. | R | Stage Gate 2: Was put on hold to redefine scope of works. | Completed | 334 day(s) late | [6 empty] | Current Forecast Spend £419345 | Stage Gate 2
PCP/15/007 | RX04F.033.201.05/06 | 172 BPR & Windsor House Chiller Remedial | Multi Sites | John Cousins | Quinten Babcock & Hakeem Makanju | Simona Kuhl | 2014-01-06 | 2014-02-06 |  | Board Date 06/02/2014 | R | [6 empty] | Cundalls | [21 empty] | BTU |  |  |  |  | 2015-09-21 | 2015-09-21 | 2017-03-20 | 2017-03-20 |  |  | BTU | G | G |  | G | 1115001 | 1027000 | 168974 | 301200 |  | -7.892% | -84.85% | G | Risk: delay due to Landlord liaison. Issues: No cooling is available and high temperatures are being experienced in parts of Windsor House. | Budget (+-): 21/01/17: crane lifts complete - risk fund can be reduced Programme: 21/01/17: BPR - Ice store to be commissioned 07/01/17. Test running to commence 06/02/17. WH - New chillers now on roof, final connections to be made. Landlord has reported a historic roof leak. | G | No Issue | [6 empty] | Forecast Completion on 20-3-2017 on time |  | Current Forecast Spend £1027000 | Stage Gate 5
PCP/15/009 | RX04F.033.201.07 | Basement Leak Detection and Sump Pump | Palestra | John Cousins | Quinten Babcock | Simona Kuhl | 2015-09-15 | 2015-10-15 |  | Board Date 15/10/2015 | R | [6 empty] | AECOM | [21 empty] | AECOM |  |  |  |  | 2016-07-22 | 2016-07-22 | 2016-12-16 | 2016-12-16 | 2016-12-16 | 2017-03-16 | BTU | G | G | G | G | 131343 | 113674 | 96973 | 81430 |  | -13.45% | -26.17% | G | Risk: No Risks Issues: No Issues | Budget (+-): 19/12/16: Risk fund released; Designer fee reduced to pay for specification error. Programme: Witness testing on 12/12/16 successful with minor snags. Completion Cert issued (with snags). | G | Practical completion envisaged 12/12/2016 | [6 empty] | Completed | on time | Under budget by £17669 | Stage Gate 5
PCP/16/006 | RX04.033.303.04 | Toilet Flushing Upgrade | Palestra | John Cousins | Quinten Babcock | Simona Kuhl | 2015-09-15 | 2015-10-15 |  | Board Date 15/10/2015 | R | [6 empty] | PRS | [15 empty] | 2016-06-01 | 2016-06-01 | 2016-08-10 | 2016-08-10 | 2016-08-10 |  | PRS | G | G | G | G | [11 empty] | 126000 | 409317 | 18935 | 126000 |  | 224.9% | -84.97% | R | Scope changed to include review of back panels and toilet operation. Risks include float installed with insufficient falls; cistern refill speed insufficient; poor quality fire stopping behind panels; poor quality electrical installation behind panels. | Budget (+-): TfL QS has prepared estimate of costs. revised cost reported. Programme: tender issued 27/01/16, return due 10/03/17, SG4 for implementation go ahead 26/04/17, completion December 2017 | R | Permission given to proceed to tender |  |  |  |  | Completed | on time |  |  | Current Forecast Spend £409317 | Stage Gate 4
PCP/16/016 | RX04F.033.301.01 | Templar House Boiler Replacement | Templar House | John Murphy | Mike O'Connor | Simona Kuhl | 2015-07-14 | 2015-08-14 |  | Board Date 14/08/2015 | R | [6 empty] | Cundalls | [26 empty] | 2016-03-07 | 2016-03-07 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2017-03-12 | Vinci FM | G | G | G | G | 179311 | 179311 | 124370 |  |  | 0% | -30.64% | G | Risk: No Risks Issues: Heating system is open without open vent and will be referred to FO/IS (R Sciberras) for technical consideration. There appears to be a BMS philosophy/control concern which has been notified to FO/IS (R Sciberras) | Budget (+-): 20/01/17: Final account submissions requested from Contractor (Vinci) possible variation due to BMS communications issues with Pier Walk server. Programme: 20/01/17: BMS issues experienced following server problems at Pier Walk. However Practical Completion agreed as boiler is operational and under BMS control although with constraints. | G | BMS to be address by FacOps | [6 empty] | Completed | on time | Under budget by £0 | Stage Gate 5
PCP/16/018 | RX04F.033.303.08 | VSH Roof and Facades Repairs | Victoria Station House | John Cousins | Hakeem Makanju | Simona Kuhl | 2015-09-22 | 2015-10-22 |  | Board Date 22/10/2015 | R | [6 empty] | Frankhams | [15 empty] | 2016-10-20 | 2016-10-20 | 2017-05-15 | 2017-05-15 |  |  | Frankhams | G | G |  | G | [11 empty] | 571000 | 571000 | 7451 |  |  | 0% | -98.7% | G | Risk: Discovery of additional works when close inspection is available. Issues: No Issues | Budget (+-): 19/12/16: Budget will be revised as specification develops. Programme: 19/12/16 Frankham feasibilty report issued on 21/12/16. This is under review. TfL response with instructions as to how to proceed required by w/c 09/01/17. No works programmed this FY. | G | Construction work to be started in 2017 financial year A variation to brief cost, and programme |  |  |  |  | Forecast Completion on 15-5-2017 on time |  |  |  | Current Forecast Spend £571000 | Stage Gate 4
PCP/16/019 | RX04F.033.303.08 | 172 BPR LV Infrastructure Upgrade | 172 Buckingham Palace Road | Laurie Morely |  | Simona Kuhl | 2015-12-17 | 2016-01-17 |  | Board Date 17/01/2016 | R | [6 empty] | Frankhams | [15 empty] | 2016-04-14 | 2016-08-06 | 2016-12-23 | 2016-12-23 | 2017-01-05 |  | Frankhams | R | G | G | G | [11 empty] | 61226 | 61226 | 50529 | 61226 |  | 0% | -17.47% | G | Complete stage gate 1; commence tender for designers and survey. Subject to finalising details with Procurment out to tender w.c. 11 April 16. Procurment issue experienced: Tender issued but not acknowledged by many on list. Flagged to procurement who confirmed problem. Procurement extended tender return date to 13 May 2016. Await return of tenders to evaluate. Tenders evaluated and agreed with Procurement. Procurment have completed their assessment. Confirmed Frankhams are successful. Updated PEP submitted to Simona on 14 June for sign off. Remainder of stage gate 3 info prepared and submitted 16 June for board on 22 June. Understood PEP not signed nor project considered at board. Await istructions. Surveys undertaken. Designs commenced. Design review meeting being set up await feedback from Frankhams. Frankhams rep in hospital afteraccident. Meeting to be arranged for w.c. 10 Oct. Design review posted for 3 Nove at which scheme will be reviewed and signed off and or altered. Anticipate design phase - end of comission will be completed by end Nov 16 | Budget (+/-): 1 week delay to programme Programme: | G | Tender Package to be sent out by 31st Janaury 2017. |  |  |  |  | Completed | 13 day(s) late |  |  | Current Forecast Spend £61226 | Stage Gate 4
FACOPS/16/001 | RX04F.033.302.02 | 172 BPR 5th Floor Power | 172 Buckingham Palace Road | John Murphy | Hakeem Makanju | Simona Kuhl | 2016-07-20 | 2016-08-20 |  | Board Date 20/08/2016 | R | [6 empty] | Powersys | [26 empty] | 2016-08-01 | 2016-08-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2017-03-01 | Powersys | G | G | G | G | 175000 | 175000 | 126281 |  |  | 0% | -27.84% | G | Risk: No Risks Issues: No Issues | Budget (+-): 20/01/17: Contractor (Powersys) account agreed without increase to Budget although formal sign off is to follow. Programme: 20/01/17 Programme maintained with PC notified as 01/12/16 to acknowledge transfer of power to new system achieved 24/11/16. | G | No Issue | [6 empty] | Completed | on time | Under budget by £0 | Stage Gate 5
Rech/16/ACR12721 | CC10284 / IO2147442 | 200 BPR New Kitchens 4th,5th and 6th Floors | 200 Buckingham Palace Road | Alan Crossan | Robert Sciberras | Christine Peppiatt | 2016-01-29 | 2016-02-29 |  | Board Date 29/02/2016 | R | [6 empty] | Baqus | [26 empty] | 2016-08-03 | 2016-08-03 | 2016-10-14 | 2016-12-05 | 2016-12-02 | 2017-03-02 | Oaklands | G | R | R | R | 135000 | 135000 | 0 | 135000 |  | 0% | -100% | G | BMS system graphics requested via email 30/12/15 - Chased 25/01/16 - to date none received. Pre-contract information lacking - no as-built information issued to date. Potential delay to start on site. Stakeholder buy-in necessary, meetings difficult due to individuals schedules. Start on site delayed by 1 week to allow for stakeholder meeting to be undertaken, and agreement achieved. Risk becomes issue - Durat worktop delivery risk, delay 2 weeks - delivery took 5 weeks, not 3 as promised by Durat. Both tea-points completed by contractor subject to snagging items. | BMS connection via main contractor cancelled due to lack of funding via Fac Ops Dept. Main Contractor instructed not to connect extract fan to BMS. Risk of delay due to Durat specified worktops coming from Helsinki. Worktop delivery did delay project completion. Anticipated additional costs for additional vinyl coverings and necessary alterations to ceiling. Previous handover meeting cancelled due to family matter. Final O&M issued by contractor - reviewed - 'As Built' drawings outstanding. Due w/c 09/05/16 Installation complete - sign off process begun. Handover meeting rearranged for wc 26/05/16. Handover meeting completed. O&M to be issued 31/05/16. O&M Issued to Fac Ops 03/06/16 - awaiting sign off. Snags received. Issued to contractor. Contractor has agreed suitable date for snag attendance. Snagging ongoing. Due for completion w/c 27/06/15. Snags completed and list issued back to Fac Ops 06/07/16 with photos and updated snag list. Sign off requested by AC. Agreed close out measures. Project Completed and Handed over 02/12/2016. Stage Gate 5 handover certificate to be completed by chairs action 05/12/2016 | R | PM to finalise costs | [6 empty] | Completed | 49 day(s) late | Under budget by £0 | Stage Gate 5
RECH/16/ACR13748 | RX04F.029.037 | 13 Allsop Place Refurbishment ex-police cells to make new into lockers | Allsop Place, 13 (NW1) | Laurie Morely |  | Christine Peppiatt | 2016-07-18 | 2016-08-18 |  | Board Date 18/08/2016 | R | [6 empty] | Fusion | [26 empty] | 2016-08-24 | 2016-10-03 | 2016-11-09 | 2016-11-18 | 2016-11-18 | 2017-02-18 |  | R | A | A | A | 174000 | 174000 | 0 | 174000 |  | 0% | -100% | G | Project submitted stage gate 1 on 20.7.16; Project submitted for stage gate 4, 2 sept. Tender evaluation completed. Contract ready to go. Procurment will not release until stage gate approval. CAR agreed and signed off. PO placed. Project was delayed to next stage gate. Due to start on site 28 sept 16, pending M&E sign off. Project delayed 1 week due to late production of RAMS for WAZ. Start on site date now 3 Oct. Project on site. PC expected 3 Nov. X rail have confirmed not occupying until 21 Nov. PC acheived on 18 Nov 16 | Project handed over - complete - snagging to pursue | G | PM to finalise costs | [6 empty] | Completed | 9 day(s) late | Under budget by £0 | Stage Gate 5
OCR/16/001 | IO2147462 | Uniform Store relocation to Penton Street | Penton Street (NW1) | Laurie Morely |  | Christine Peppiatt | 2016-08-29 | 2016-09-29 |  | Board Date 29/09/2016 | R | [33 empty] | 2016-10-28 | 2016-11-01 | 2016-12-23 | 2016-12-23 | 2016-12-20 | 2017-03-20 |  | G | G | G | G | 1333000 | 1333000 | 0 | 1333000 |  | 0% | -100% | G | Tender docs assembled. Contractors enquiry ready to go. Await procurement approval to strategy docuemnt requested. In hand. Out to tender. Project on site as of 31/12/16 pending WAR approvals. | Currently on programme | G | PM to finalise costs | [6 empty] | Completed | 3 day(s) early | Under budget by £0 | Stage Gate 5
Rech/15/ACR10787 |  | LSTOC Accommodation Workstream | Palestra | Tony Hunter |  | Nicky Mahood | 2015-01-01 | 2015-02-01 |  | Board Date 01/02/2015 | R | [6 empty] | PRS, Furness Green, Sandy Brown | [26 empty] | 2015-07-04 | 2015-07-04 | 2016-11-23 | 2016-11-23 | 2016-08-11 | 2016-11-11 | London Fit Out | G | G | G | G | 647000 | 479000 | 0 |  |  | -25.97% | -100% | G |  | Fac Ops handover inspections undertaken for both sites. LSTOC went operational on 1 Sep '16. Variation to extend completion date to cover return visit has been issued. Close out activities: 2 items preventing project closure (PCR) - (1) Quote from Mitie to amend 200BPR BMS headend to show new partition; implementation could be post-PCR once PO has been raised. & (2) alteration of O&M to reflect Infrstructure team feedback - contractor has done incorrectly and rectification measures in place. STAKEHOLDER COMMENTS: Issue Change Request - Need Tony to come to next meeting, update forecast | G | Stage Gate 5 over due by 39 days | [6 empty] | Completed | 104 day(s) early | Under budget by £168000 | Stage Gate 5
Rech/16/ACR6446 | IO2146323 | New Meeting Rooms for Steve Burton EOS Director | Palestra | Martina Perkins |  | Nicky Mahood | 2016-04-18 | 2016-05-18 |  | Board Date 18/05/2016 | R | [33 empty] | 2016-11-18 | 2015-11-18 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2017-03-07 |  | G | G | G | G | 215160 | 155871 | 0 |  |  | -27.56% | -100% | G |  | Nicky Mahood agreed final account/variations with FM Conway and will be closing this project. | G | No Issue | [6 empty] | Completed | on time | Under budget by £59289 | Stage Gate 5
Rech/16/ACR14011 | RX04F.033.303.10 | 2nd Floor Kitchen area Palestra | Palestra | Martina Perkins |  | Simona Kuhl | 2016-07-25 | 2016-08-25 |  | Board Date 25/08/2016 | R | [33 empty] | 2017-01-09 | 2017-01-09 | 2017-02-13 | 2017-02-13 | 2017-01-21 | 2017-04-21 |  | G | G | G | G | 42000 | 42000 | 0 |  |  | 0% | -100% | G | * Vinyl floor - lifting vinyl floor may damage suspended tiles underneath which may result with project delay (1 week) + additional cost (project risk allowance to cover). | Project started. We should know by the end of the working date (09.01.2017) if the potential risk has materialised. Risk not materialised. Practical completion achieved on 21.01.2017. | G | No Issue | [6 empty] | Completed | 23 day(s) early | Under budget by £0 | Stage Gate 5
Rech/16/ACR10994 | IO2147043 | Templar House Basement Changeing Room for Chancery Lane Escalator Replacement Project | Templar House | Martin Smith |  | Christine Peppiatt | 2016-01-01 | 2016-02-01 |  | Board Date 01/02/2016 | R | [35 empty] | 2016-02-15 | 2016-02-15 | 2016-02-15 | 2016-05-15 |  | G | G | G | G |  |  | 0 |  |  | #DIV/0! | #DIV/0! |  |  | Project hand over certificate issued on 30/12/2016 Rob Sciberras has handed project over to Michael O'Connor on departure. Meeting arranged Martin Smith / Michael O'Connor for Thursday 19th January on site to review project and discuss handover certificate. Stage Gate 5 Close Out Report to be prepared in anticipation of handover. | G | Stage gate 5 overdue by 239 days Issue a close out report noting the low quality drawings any new drawings will have to be a new project waiting on accounts payable to find out where final payment went | [9 empty] | Stage Gate 5
PCP/16/024 |  | Griffith House Facade Repairs | Griffith House (NW1) | John Cousins | Dave Parr | Simona Kuhl | 2016-11-15 | 2017-01-18 |  | Board Date 18/01/2017 | R | [44 empty] | 288000 | 288000 | 0 | 288000 |  | 0% | -100% | G | Project initiation meeting to be held | Budget (+-): 19/12/16: Budget to be developed, but expected to be c. £750,000 Programme: 19/12/16 programme to be developed to prioritise urgent repairs. Structural Engineer to be appointed to specify repair actions. | G | Stage Gate 1 date has now been missed. Project Manger to submit at the next board meeting 1st February 2017. | [8 empty] | Current Forecast Spend £288000 | Stage Gate 1
PCP/16/023 |  | Broadway PA/VA system | Broadway Complex | Helena Healy | Dave Parr | Simona Kuhl | 2016-11-15 | 2017-01-18 | 2017-01-18 | Completed 18/01/2017 | G | [33 empty] | 2017-03-20 | 2017-03-20 | 2017-04-04 | 2017-04-04 |  |  |  | G | G |  | G | 84500 | 84500 | 0 | 845000 |  | 0% | -100% | G |  | Pell Frishmann have declined to provide a Fee for PD role awaiting cost from Cundalls. The budget for this project will be 100k. Stage Gate 1 documentation sent to the PMO on 30/12/2016 for Board meeting date 18/01/2017 | G | Stage 1-4 has been approved. | [6 empty] | Forecast Completion on 4-4-2017 on time |  | Current Forecast Spend £84500 | Stage Gate 5
RECH/16/ACR8658 |  | 4L Emergancy Service Control Centre | Baker Street, 210-212 (NW1) | Tony Hunter |  | Christine Peppiatt | 2017-01-05 | 2017-02-05 |  | Board Date 05/02/2017 | G | [44 empty] | 85368 | 85368 | #N/A | 85368 |  | 0% | #N/A | #N/A |  |  | #N/A | 0 | [8 empty] | Current Forecast Spend £85368 | Stage Gate 1
RECH/16/ACR16145 |  | Bringing Back to use Staircase/chained door leading to the track | Griffith House (NW1) | Martina Perkins |  | Amanda Morrison | [38 empty] | 2017-03-20 | 2017-03-20 | 2017-04-03 | 2017-04-03 |  |  |  | G | G |  | G | 107100 | 107100 | #N/A |  |  | 0% | #N/A | #N/A |  |  | #N/A | 0 | [6 empty] | Forecast Completion on 3-4-2017 on time |  | Current Forecast Spend £107100 | Stage Gate 5
[58 empty] | #N/A |  |  | #DIV/0! | #N/A |  |  |  |  | 0 | [9 empty] | Stage Gate 1
[58 empty] | #N/A |  |  | #DIV/0! | #N/A |  |  |  |  | 0 | [9 empty] | Stage Gate 1
[58 empty] | #N/A |  |  | #DIV/0! | #N/A |  |  |  |  | 0 | [9 empty] | Stage Gate 1
[58 empty] | #N/A |  |  | #DIV/0! | #N/A |  |  |  |  | 0 | [9 empty] | Stage Gate 1
[58 empty] | #N/A |  |  | #DIV/0! | #N/A |  |  |  |  | 0 | [9 empty] | Stage Gate 1
[58 empty] | #N/A |  |  | #DIV/0! | #N/A |  |  |  |  | 0 | [9 empty] | Stage Gate 1
[58 empty] | #N/A |  |  | #DIV/0! | #N/A |  |  |  |  | 0 | [9 empty] | Stage Gate 1
[58 empty] | #N/A |  |  | #DIV/0! | #N/A |  |  |  |  | 0 | [9 empty] | Stage Gate 1
[58 empty] | #N/A |  |  | #DIV/0! | #N/A |  |  |  |  | 0 | [9 empty] | Stage Gate 1
[58 empty] | #N/A |  |  | #DIV/0! | #N/A |  |  |  |  | 0 | [9 empty] | Stage Gate 1
[58 empty] | #N/A |  |  | #DIV/0! | #N/A |  |  |  |  | 0 | [9 empty] | Stage Gate 1
[58 empty] | #N/A |  |  | #DIV/0! | #N/A |  |  |  |  | 0 | [9 empty] | Stage Gate 1
[58 empty] | #N/A |  |  | #DIV/0! | #N/A |  |  |  |  | 0 | [9 empty] | Stage Gate 1
[58 empty] | #N/A |  |  | #DIV/0! | #N/A |  |  |  |  | 0 | [9 empty] | Stage Gate 1
[58 empty] | #N/A |  |  | #DIV/0! | #N/A |  |  |  |  | 0 | [9 empty] | Stage Gate 1
[58 empty] | #N/A |  |  | #DIV/0! | #N/A |  |  |  |  | 0 | [9 empty] | Stage Gate 1
Formulas:
Forecast Board Date = IF([Stage Gate 1]="","",DATE(YEAR([Stage Gate 1]),MONTH([Stage Gate 1])+1,DAY([Stage Gate 1])))
Forecast Board Date = IF([Stage Gate 1]="","",DATE(YEAR([Stage Gate 1]),MONTH([Stage Gate 1])+2,DAY([Stage Gate 1])+3))
Rag Status = IF(AND([Actual Board Date]="",[Forecast Board Date]=""),"",IF(AND([Actual Board Date]="",[Forecast Board Date]<TODAY()),"R","G"))
Note on D2: veronicasenior: Choose from drop down menu
Note on E2: veronicasenior: Choose from drop down menu
Note on G2: veronicasenior: Insert from drop down menu

## Health and Saftey
Health and Safety Documentation
Project ID | WBS Element | Project Name | Building | Project Manager | Competent Principal Designer | Competent Principal Contractor | F10 Notifications and Renotifications | Written Principal Designer Appointment | Written Principal Contractor Appointment | Designer General Principals of Prevention | Preconstruction Information | Construction Phase Plan | Asbestos Impact Assessment (AIA) | Competency of Site Manager | Construction Site Inspections | Health and Safety File | NEC3 Form Contract
PCP/12/033 | RX04F.014.2007.708.02 | Albany House - Plant Optimisation | Albany House | Jerry Young | N/A | YES | N/A | N/A | N/A | N/A | N/A | N/A | YES | NO | N/A | NO | N/A
| RX04F.014.2007.708.02 | Albany House - Plant Optimisation | Albany House | Jerry Young | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
PCP/15/003 | RX04F.014.2007.903.01 | Victoria Station House Fire Doors | Victoria Station House | John Cousins | YES | YES | N/A | YES | YES | N/A | YES | yes | YES | YES | N/A | YES | YES
| RX04F.014.2007.903.01 | Victoria Station House Fire Doors | Victoria Station House | John Cousins | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM | 09.05 Audit & Inspection | 09.03 Health and Saftely File
PCP/15/006 | RX04F.014.2007.903.03 | Baker Street Complex - Fire Compliance - Fire Alarms no MICC | Baker Street | Jerry Young | YES | YES | YES | YES | YES | N/A | YES | YES | YES | NO | N/A | NO | N/A
| RX04F.014.2007.903.03 | Baker Street Complex - Fire Compliance - Fire Alarms no MICC | Baker Street | Jerry Young | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM | 09.05 Audit & Inspection | 09.03 Health and Saftely File
PCP/15/007 | RX04F.033.201.05 / 06 | 172 BPR & Windsor House - Chillers Remedial | Windsor House | John Cousins | YES | YES | N/A | YES | YES | N/A | N/A | YES | YES | YES | N/A | N/A | YES
| RX04F.033.201.05 / 06 | 172 BPR & Windsor House - Chillers Remedial | Windsor House | John Cousins | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM | 09.05 Audit & Inspection | 09.03 Health and Saftely File
PCP/15/009 | RX04F.033.201.07 | Basement Leak Detection and Sump Pump | Palestra | John Cousins | YES | YES | N/A | YES | YES | N/A | YES | YES | N/A | YES | N/A | YES | YES
| RX04F.033.201.07 | Basement Leak Detection and Sump Pump | Palestra | John Cousins | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM |  | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
PCP/16/006 | RX04F.033.303.04 | Toilet Flushing Upgrade | Palestra | John Cousins | YES | YES | N/A | YES | N/A | N/A | YES | N/A | N/A | N/A | N/A | N/A | N/A
| RX04F.033.303.04 | Toilet Flushing Upgrade | Palestra | John Cousins | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
PCP/16/007 | RX04F.033.303.02 | 200 BPR Toilet Refurbishment | 200 BPR | John Murphy | N/A | N/A | N/A | N/A | N/A | N/A | YES | N/A | N/A | N/A | N/A | N/A | N/A
| RX04F.033.303.02 | 200 BPR Toilet Refurbishment | 200 BPR | John Murphy | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
PCP/16/010 | RX04F.033.303.03 | Refurbishment Griffith House | Griffiths House | Helena Healy | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RX04F.033.303.03 | Refurbishment Griffith House | Griffiths House | Helena Healy | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
PCP/16/016 | RX04F.033.301.01 | Templar House - Boiler Replacement | Templar House | John Murphy | YES | YES | N/A | YES | YES | N/A | YES | YES | YES | N/A | N/A | YES | N/A
| RX04F.033.301.01 | Templar House - Boiler Replacement | Templar House | John Murphy | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
PCP/16/018 | RX04F.033.303.08 | VSH Roof and Facade Repair | Victoria Station House | John Murphy | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RX04F.033.303.08 | VSH Roof and Facade Repair | Victoria Station House | Martin Smith | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
PCP/16/019 | RX04F.033.302.06 | 172 BPR LV Infrastructure Upgrade | 172 BPR | Laurie Morley | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RX04F.033.302.06 | 172 BPR LV Infrastructure Upgrade | 172 BPR | Laurie Morley | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
PCP/16/020 | RX04F.033.307.01 | Building Facade Risk Assessment (7 Buildings) | Multisite | John Murphy | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RX04F.033.307.01 | Building Facade Risk Assessment (7 Buildings) | Multisite | John Murphy | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
FACOPS/16/001 | RX04F.033.302.02 | 172 BPR 5th Floor Power | 172 BPR | John Murphy | YES | YES | N/A | YES | YES | N/A | YES | YES | YES | N/A | N/A | YES | YES
| RX04F.033.302.02 | 172 BPR 5th Floor Power | 172 BPR | John Murphy | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
PCP/16/022 | RX04F.033.305.02 | Penton Street Upper Roof | Penton Street | Helena Healy | YES | YES | NO | YES | YES | N/A | YES | YES | YES | YES | N/A | YES | N/A
| RX04F.033.305.02 | Penton Street Upper Roof | Penton Street | Helena Healy | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
Rech/16/ACR12908 | CC20418 | Industrial Kitchen/Rest Room Refurbishment | Griffiths House | Martina Perkins | N/A | YES | N/A | N/A | NO | N/A | YES | YES | YES | YES | N/A | YES | N/A
| CC20418 | Industrial Kitchen/Rest Room Refurbishment | Griffiths House | Martina Perkins | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
Rech/15/ACR10787 | 0 | LSTOC Accommodation Workstream | Palestra & 200BPR | Tony Hunter | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 0 | LSTOC Accommodation Workstream | Palestra & 200BPR | Tony Hunter | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
Rech/15/ACR10556-10722 | 0 | Removal of existing partitions to form new larger open plan office for Commercial Strategy & Performance team 17th Floor | Windsor House | Martin Smith | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 0 | Removal of existing partitions to form new larger open plan office for Commercial Strategy & Performance team 17th Floor | Windsor House | Martin Smith | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
Rech/16/ACR10994 | IO 2147043 | Templar House Basement Changing Room for Chancery Lane Escalator Replacement Project | Templar House | Martin Smith | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| IO 2147043 | Templar House Basement Changing Room for Chancery Lane Escalator Replacement Project | Templar House | Martin Smith | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
Rech/16/ACR11245 | CC11000 | Templar House Tea points | Templar House | Alan Crossan | YES | YES | NO | N/A | N/A | N/A | YES | NO | YES | NO | N/A | YES | N/A
| CC11000 | Templar House Tea points | Templar House | Alan Crossan | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
Rech/16/ACR12721 | CC 10284 | 200 BPR New Kitchens 4th 5th 6th Floor | 200 BPR | Alan Crossan | YES | YES | N/A | YES | YES | N/A | YES | N/A | YES | YES | N/A | N/A | N/A
| CC 10284 | 200 BPR New Kitchens 4th 5th 6th Floor | 200 BPR | Alan Crossan | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
Rech/16/ACR6446 | IO 2146323 | New meeting rooms for Steve Burton EOS Director | Palestra | Martina Perkins | YES | YES | N/A | YES | YES | N/A | YES | YES | YES | YES | N/A | YES | N/A
| IO 2146323 | New meeting rooms for Steve Burton EOS Director | Palestra | Martina Perkins | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
Rech/16/ACR7149 | RX04F.036.002 | RNC Relocation to Palestra; Varied to include Reinstatement Works at 55 Broadway | Palestra / 55 Broadway | Martin Smith | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RX04F.036.002 | RNC Relocation to Palestra; Varied to include Reinstatement Works at 55 Broadway | Palestra / 55 Broadway | Martin Smith | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
Rech/16/ACR7149 | RX04F.033.303.09 | RNC Relocation to Palestra; Varied to include Reinstatement Works at 55 Broadway | Palestra / 55 Broadway | Martin Smith | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RX04F.033.303.09 | RNC Relocation to Palestra; Varied to include Reinstatement Works at 55 Broadway | Palestra / 55 Broadway | Martin Smith | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
Rech/16/ACR13748 | RX04F.029.037 | 13 Allsop Place Refurbishment ex-police cells to make new Locker rooms X-Rail | 0 | Laurie Morley | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RX04F.029.037 | 13 Allsop Place Refurbishment ex-police cells to make new Locker rooms X-Rail | 0 | Laurie Morley | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
OCR/16/001 | IO 2147462 | Uniform store relocation to Penton Street | 0 | Laurie Morley | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| IO 2147462 | Uniform store relocation to Penton Street | 0 | Laurie Morley | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
PCP/16/017 | RX04F.033.302.01 | Palestra-Power Integration Project | Palestra | Andrew Jefferies | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RX04F.033.302.01 | Palestra-Power Integration Project | Palestra | Andrew Jefferies | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
PCP/16/021 | RX04F.033.307.02 | Safety Replacement of Meeting Chairs | Multisite | Gary Evans | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| RX04F.033.307.02 | Safety Replacement of Meeting Chairs | Multisite | Gary Evans | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
Rech/16/ACR14011 | RX04F.033.303.10 | 2nd Floor Kitchen area Palestra | Palestra | Martina Perkins | N/A | YES | N/A | N/A | YES | N/A | YES | YES | N/A | YES | N/A | YES | YES
| IO 21300220 | 2nd Floor Kitchen area - Palestra | Palestra | Martina Perkins | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
PCP/16/024 | 0 | Griffith House Facade Repairs | Griffith House (NW1) | John Cousins | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 0 | Griffith House Facade Repairs | Griffith House (NW1) | John Cousins | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File
PCP/16/023 | 0 | Broadway PA/VA system | Broadway Complex | Helena Healy | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| 0 | Broadway PA/VA system | Broadway Complex | Helena Healy | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.01 CDM | 09.02 Health & Safety Plan | 09.02 Health & Safety Plan | 09.01 CDM |  | 09.03 Health and Safety File

## Stage Gate 5
Projct ID | Project Name | Project Manager | Contractual Practical Completion | Stage Gate 5 Completion | Days Until Stage 5 Completion | Submitted to Stage Gate 5 Board
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
Rech/16/ACR10994 | Templar House Basement Changeing Room for Chancery Lane Escalator Replacement Project | Martin Smith | 2016-02-15 | 2016-05-15 | -263 | NO
Rech/15/ACR10787 | LSTOC Accommodation Workstream | Tony Hunter | 2016-08-11 | 2016-11-11 | -83 | NO
RECH/16/ACR13748 | 13 Allsop Place Refurbishment ex-police cells to make new into lockers | Laurie Morely | 2016-11-18 | 2017-02-18 | 16 | NO | 280
FACOPS/16/001 | 172 BPR 5th Floor Power | John Murphy | 2016-12-01 | 2017-03-01 | 27 | NO | 293
Rech/16/ACR12721 | 200 BPR New Kitchens 4th,5th and 6th Floors | Alan Crossan | 2016-12-02 | 2017-03-02 | 28 | NO
Rech/16/ACR6446 | New Meeting Rooms for Steve Burton EOS Director | Martina Perkins | 2016-12-07 | 2017-03-07 | 33 | NO
PCP/16/016 | Templar House Boiler Replacement | John Murphy | 2016-12-12 | 2017-03-12 | 38 | NO
PCP/15/009 | Basement Leak Detection and Sump Pump | John Cousins | 2016-12-16 | 2017-03-16 | 42 | NO
PCP/16/023 | Broadway PA/VA system | Helena Healy | 0 |  | #VALUE! | NO
Rech/16/ACR14011 | 2nd Floor Kitchen area Palestra | Martina Perkins | 2017-01-21 | 2017-04-21 | 78 | NO
RECH/16/ACR8658 | 4L Emergancy Service Control Centre | Tony Hunter | 0 |  | #VALUE! | NO
RECH/16/ACR16145 | Bringing Back to use Staircase/chained door leading to the track | Martina Perkins | 0 |  | #VALUE! | NO
OCR/16/001 | Uniform Store relocation to Penton Street | Laurie Morely | 2016-12-20 | 2017-03-20 | 46 | NO
PCP/12/033 | Albany House - Plant Optimisation | Jerry Young | 0 |  | #VALUE!
PCP/15/006 | Baker Street Complex - Fire Compliance - Fire Alarms no MICC | Jerry Young | 0 |  | #VALUE! | NO
PCP/16/020 | Building Facades Risk Assessments (7 Building) | John Murphy | 0 |  | #VALUE! | NO
PCP/16/007 | 200 BPR Toilet Refurbishment | John Murphy | 0 |  | #VALUE! | NO
PCP/15/007 | 172 BPR & Windsor House Chiller Remedial | John Cousins | 0 |  | #VALUE! | NO
PCP/16/006 | Toilet Flushing Upgrade | John Cousins | 0 |  | #VALUE! | NO
PCP/16/018 | VSH Roof and Facades Repairs | John Cousins | 0 |  | #VALUE! | NO
PCP/16/019 | 172 BPR LV Infrastructure Upgrade | Laurie Morely | 0 |  | #VALUE! | NO
PCP/16/024 | Griffith House Facade Repairs | John Cousins | 0 |  | #VALUE!
0 | 0 | 0 | 0 |  | #VALUE!
0 | 0 | 0 | 0 |  | #VALUE!
0 | 0 | 0 | 0 |  | #VALUE!
0 | 0 | 0 | 0 |  | #VALUE!
0 | 0 | 0 | 0 |  | #VALUE!
0 | 0 | 0 | 0 |  | #VALUE!
0 | 0 | 0 | 0 |  | #VALUE!
0 | 0 | 0 | 0 |  | #VALUE!
0 | 0 | 0 | 0 |  | #VALUE!
0 | 0 | 0 | 0 |  | #VALUE!
0 | 0 | 0 | 0 |  | #VALUE!
0 | 0 | 0 | 0 |  | #VALUE!
0 | 0 | 0 | 0 |  | #VALUE!
0 | 0 | 0 | 0 |  | #VALUE!
0 | 0 | 0 | 0 |  | #VALUE!
Formulas:
Days Until Stage 5 Completion = IF([Stage Gate 5 Completion]=0,"",[Stage Gate 5 Completion]-TODAY())
Refresh Report

## Closed Projects (Stage Gate 6)
Project Detail | [6 empty] | Rentention and Release | [6 empty] | Project Finance
Projct ID | WBS Element | Project Name | Building | Project Manager | Facilities Operations | Project Sponsor | Contractor | Contractual practical completion | Defects liablity Period (Months) | Retention Release Date | Retention Amount |  | Retention Released | Approved Budget | EFC Forecast | YTD | Initial Budget | Outturn Cost
Rech/15/ACR10556-10722 |  | Removal of existing partitions to form new larger open plan office for Commercial Strategy & Performance team 17th Floor | Windsor House Complex | Martin Smith |  | Nicky Mahood |  | 2015-10-14 | 0 | 2015-10-13 | 0 | Green | YES | #N/A | #N/A | #N/A | #N/A | #N/A
Rech/16/ACR10994 | IO2147043 | Templar House Basement Changeing Room for Chancery Lane Escalator Replacement Project | Templar House | Martin Smith |  | Christine Peppiatt |  | 2016-02-15 | 0 | 2016-02-14 | 0 | Green | YES | 0 | 0 | 0 | 0 | 0
Rech/16/ACR11245 | CC11000 | Templar House Tea Points | Templar House | Alan Crossan |  | Christine Peppiatt |  | 2016-03-11 | 0 | 2016-03-10 | 0 | Green | YES | #N/A | #N/A | #N/A | #N/A | #N/A
Rech/16/ACR7149 | RX04F.033.303.09 | RNC Relocation to Palestra Varied to include Reinstatement Works at 55 Broadway | Multi Sites | Martin Smith |  | Christine Peppiatt |  | 2016-09-06 | 0 | 2016-09-05 | 0 | Green | YES | #N/A | #N/A | #N/A | #N/A | #N/A
Rech/16/ACR12908 | CC20418 | Industrial Kitchen/Rest Room Refurbishment | Griffith House (NW1) | Martina Perkins |  | Simona Kuhl |  | 2016-11-15 | 0 | 2016-11-14 | 0 | Green | Yes | 70000 | 27000 | 26302.86
Rech/16/ACR6446 | IO2146323 | New Meeting Rooms for Steve Burton EOS Director | Palestra | Martina Perkins |  | Nicky Mahood |  | 2016-12-07 | 0 | 2016-12-06 | 0 | Green | Yes | 215160 | 155871 | 0 | 0 | 0
Rech/16/ACR12721 | CC10284 / IO2147442 | 200 BPR New Kitchens 4th,5th and 6th Floors | 200 Buckingham Palace Road | Alan Crossan |  | Christine Peppiatt |  | 2016-12-02 | 6 | 2017-06-01 | 0 | Green | NO | 135000 | 135000 | 0 | 135000 | 0
PCP/16/017 | RX04F.033.302.01 | Palestra-Power Integration Project | Palestra | Andrew Jefferies |  | Simona Kuhl |  | 2016-07-01 | 0 | 2016-06-30 | 0 | Green | YES | #N/A | #N/A | #N/A | #N/A | #N/A
PCP/15/003 | RX04F.014.2007.903.01 | Victoria Station House Fire Doors | Victoria Station House | John Cousins |  | Simona Kuhl |  | 2016-08-22 | 12 | 2017-08-22 | 2439.12 | Green | NO | 114918 | 104215 | 102415 | 50433 | 104215
Rech/15/ACR10787 |  | LSTOC Accommodation Workstream | Palestra | Tony Hunter |  | Nicky Mahood |  | 2016-08-31 | 12 | 2017-08-30 |  | Green | NO | 647000 | 479000 | 0 | 0 | 0
Rech/16/ACR7149 | RX04F.036.002 | RNC Relocation to Palestra Varied to include Reinstatement Works at 55 Broadway | Multi Sites | Martin Smith |  | Christine Peppiatt |  | 2016-09-06 | 12 | 2017-09-05 | 1062.5 | Green | NO | #N/A | #N/A | #N/A | #N/A | #N/A
PCP/16/022 | RX04F.033.302.02 | Penton Street Upper Roof | Penton Street (NW1) | Helena Healy |  | Simona Kuhl |  | 2016-11-11 | 12 | 2017-11-10 | 2935.65 | Green | NO | 140000 | 125711.65 | 131096 | 140000
RECH/16/ACR13748 | RX04F.029.037 | 13 Allsop Place Refurbishment ex-police cells to make new into lockers | Allsop Place, 13 (NW1) | Laurie Morely |  | Christine Peppiatt |  | 2016-11-18 | 12 | 2017-11-17 |  | Green | NO | 174000 | 174000 | 0 | 174000 | 0
FACOPS/16/001 | RX04F.033.302.02 | 172 BPR 5th Floor Power | 172 Buckingham Palace Road | John Murphy |  | Simona Kuhl |  | 2016-12-01 | 12 | 2017-12-01 | 3428.63 | Green | NO | 175000 | 175000 | 126281 | 0 | 0
PCP/16/016 | RX04F.033.301.01 | Templar House Boiler Replacement | Templar House | John Murphy | Mike O'Connor | Simona Kuhl |  | 2016-12-12 | 12 | 2017-12-11 |  | Green | NO | 179311 | 179311 | 124370
PCP/15/009 | RX04F.033.201.07 | Basement Leak Detection and Sump Pump | Palestra | John Cousins | Quinten Babcock | Simona Kuhl |  | 2016-12-16 | 12 | 2017-12-15 |  | Green | NO | 131343 | 113674 | 96973 | 81430
[10 empty] | Total | 9865.9
Formulas:
Retention Release Date = IF([Defects liablity Period (Months)]="","",DATE(YEAR([Contractual practical completion]),MONTH([Contractual practical completion])+[Defects liablity Period (Months)],DAY([Contractual practical completion])-1))
Retention Release Date = IF([Defects liablity Period (Months)]="","",DATE(YEAR([Contractual practical completion]),MONTH([Contractual practical completion])+[Defects liablity Period (Months)],DAY([Contractual practical completion])))
Note on D2: veronicasenior: Choose from drop down menu
Note on E2: veronicasenior: Choose from drop down menu
Note on G2: veronicasenior: Insert from drop down menu

## Archive
Project Detail | [6 empty] | Stage Gate 1 |  |  |  |  | Feasibility Stage Gate 2 | [10 empty] | Design Stage Gate 3 | [10 empty] | Design Stage Gate 4 | [10 empty] | Construction Stage Gate 5 | [10 empty] | Project Finance | [7 empty] | Project Comments |  | Status and Comments |  | Calculations
Projct ID | WBS Element | Project Name | Building | Project Manager | Facilities Operations | Project Sponsor | Handover Date | Forcast Board Date | Actual Board Date |  | Rag Status | Baseline Start | Actual Start | Baseline Completion | Forecast Completion | Actual Completion | Stage Gate 2 Completion | Consultant | Actual Start | Forecast Completion | Actual Completion | RAG Status | Baseline Start | Actual Start | Baseline Completion | Forecast Completion | Actual Completion | Stage Gate 3 Completion | Designer | Actual Start | Forecast Completion | Actual Completion | RAG Status | Baseline Start | Actual Start | Baseline Completion | Forecast Completion | Actual Completion | Stage Gate 4 Completion | Designer | Actual Start | Forecast Completion | Actual Completion | RAG Status | Baseline Start | Actual Start | Baseline Completion | Forecast Completion | Contractual Practical Completion | Stage Gate 5 Completion | Contractor | Actual Start | Forecast Completion | Actual Completion | RAG Status | Approved Budget | EFC Forecast | YTD | Initial Budget | Outturn Cost |  |  | RAG Status | Risk & Issues: | Current Comments | Project Overall RAG Status | Stakeholder Comments | Stage Gate 2 Status | Overrun? | Stage Gate 3 Status | Overrun? | Stage Gate 4 Status | Overrun? | Stage Gate 5 Status | Overrun? | Finance | Stage Gate
Rech/16/ACR12908 | CC20418 | Industrial Kitchen/Rest Room Refurbishment | Griffith House (NW1) | Martina Perkins |  | Simona Kuhl | [38 empty] | 2016-07-22 | 2016-07-22 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2017-02-15 |  | G | G | G | G | 70000 | 27000 | 26302.86 |  |  | -61.43% | -62.42% | G |  | * Stage Gate 5 approved. * Stage Gate 6 submitted on Friday 25/11/2016. *The project should be removed from the tracker's live projects. | G | [7 empty] | Completed | on time | Under budget by £43000
PCP/15/003 | RX04F.014.2007.903.01 | Victoria Station House Fire Doors | Victoria Station House | John Cousins |  | Simona Kuhl | [33 empty] | Door View |  |  |  |  | 2016-05-23 | 2016-04-30 | 2016-08-29 | 2016-08-22 | 2016-08-22 | 2016-11-22 | JNG Ltd | G | G | G | G | 114918 | 104215 | 102415 | 50433 |  | -9.314% | -10.88% | G | Risks have been released. Several hinges have had hinge pins come loose. The manufacturer has visited site to inspect and has taken a sample defect. Report and proposal awaited from JNG. | Budget (+-): Final account agreed with JNG. Programme: O&Ms revised and agreed. H&S File submitted. PCHC signed. Gate 5 documents submited for review on 23rd November 2016. | G | [7 empty] | Completed | 7 day(s) early | Under budget by £10703
PCP/16/022 | RX04F.033.302.02 | Penton Street Upper Roof | Penton Street (NW1) | Helena Healy | Robert Sciberras | Simona Kuhl | 2016-09-07 | 2016-10-07 | [9 empty] | John Cobbs | [22 empty] | Vinci FM | G | 140000 |  | 2016-09-19 | 2016-09-19 | 2016-11-30 | 2016-11-30 | 2016-11-11 | 2017-02-11 | Vinci FM | G | Remove from Tracker sheet transfer to archive and stage gate 6 sheet |  | Remove from Tracker sheet transfer to archive and stage gate 6 sheet | 140000 | 125711.65 | 131096 | 140000 |  | -10.21% | -6.36% | G |  | Budget (+/-): Completed under budget. Programme: Completed ahead Programme. Stage Gate 5 achieved on 04/01/2017. | G
PCP/16/017 | RX04F.033.302.01 | Palestra-Power Integration Project | Palestra | Andrew Jefferies |  | Simona Kuhl | 2016-01-01 | 2016-02-01 |  | Board Date 01/02/2016 | R | [33 empty] | 2015-11-07 | 2015-12-05 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-10-01 |  | A | G | G | G | 136300 | 94253 | 47466 |  |  | -30.85% | -65.18% | G |  |  | G | [7 empty] | Completed | on time | Under budget by £42047
Rech/16/ACR7149 | RX04F.036.002 | RNC Relocation to Palestra Varied to include Reinstatement Works at 55 Broadway | Multi Sites | Martin Smith |  | Christine Peppiatt | 2016-01-01 | 2016-02-01 |  | Board Date 01/02/2016 | R | [35 empty] | 2016-06-06 | 2016-06-06 | 2016-09-06 | 2016-12-06 |  | G | G | G | G |  |  | 0 |  |  | #DIV/0! | #DIV/0! |  |  | Handover Certificate issued 30/12/2016 supported by Stage Gate 5 Close Out Report. Handover Certifcate reviewed David Parr / Ray Edwards 06/01/2017, copy of snag sheets requested 06/01/2016 and supplied 12/01/2017. Awaiting handover certifcate to be signed | G | Needs to issue paperwork for Stage gate 5 Next board to close out 18/01/2017 stage gate 5 overdue by 34 | [9 empty] | Stage Gate 5
Rech/16/ACR7149 | RX04F.033.303.09 | RNC Relocation to Palestra Varied to include Reinstatement Works at 55 Broadway | Multi Sites | Martin Smith |  | Christine Peppiatt | 2016-01-01 | 2016-02-01 |  | Board Date 01/02/2016 | R | [35 empty] | 2016-06-06 | 2016-06-06 | 2016-09-06 | 2016-12-06 |  | G | G | G | G |  |  | 0 |  |  | #DIV/0! | #DIV/0! |  |  | Handover Certificate issued 30/12/2016 supported by Stage Gate 5 Close Out Report. Handover Certifcate reviewed David Parr / Ray Edwards 06/01/2017, copy of snag sheets requested 06/01/2016 and supplied 11/01/2017. Awaiting handover certifcate to be signed | G | Needs to issue paperwork for Stage gate 5 Next board to close out 18/01/2017 stage gate 5 overdue by 34 | [9 empty] | Stage Gate 5
Rech/16/ACR11245 | CC11000 | Templar House Tea Points | Templar House | Alan Crossan |  | Christine Peppiatt | 2016-01-01 | 2016-02-01 |  | Board Date 01/02/2016 | R | [33 empty] | 2016-02-01 | 2016-02-01 | 2016-02-22 | 2016-03-11 | 2016-03-11 | 2016-06-11 |  | G | R | R | R | 44000 | 37400 | 0 | 25000 |  | -15% | -100% | G | Current risk: IM not agreeing to strategy of running services pipe-work through IM room. Currently designing out the risk for agreement. IM agreement to route forward. Design agreed. Risk: Current draft costplan higher than originally anticipated due to additional DDA requirements and necessary alterations to IM room to mitigate risk of leaking pipe-work. Risk of project cancellation if deemed too high a cost by project sponsor. Project currently out to tender o ratify budget. Client liaison necessary due to costplan estimate being higher than anticipated originally. Tenders returned. Costs issued to MN to obtain financial authority. Financial authority 95% completed. Meeting arranged for final sign off of design 23/06/17. AC redesign complete and contractor agreement obtained to costs. | Authority for Board submission received. Submission due 01/07/16. Stage 4 approval Submission due 01/07/16. Stage Gate 4 success and approval to proceed received. Pre-Start meeting convened 17/07/16. Fujitsu to complete enabling works by 31/07/16 - main contractor start on site 01/08/16. Works duration 10 weeks. Actual start on site: 03/08/16 Stage Gate 5 Waiting on Operation representative to sign off handover certificate. Will be completed by chairs actions | R | Stage gate 5 over due by 212 days | [6 empty] | Completed | 18 day(s) late | Under budget by £6600 | Stage Gate 5
Rech/15/ACR10556-10722 |  | Removal of existing partitions to form new larger open plan office for Commercial Strategy & Performance team 17th Floor | Windsor House Complex | Martin Smith |  | Nicky Mahood | 2015-01-01 | 2015-02-01 |  | Board Date 01/02/2015 | R | [35 empty] | 2015-10-05 | 2015-10-14 | 2015-10-14 | 2016-01-14 |  | G | G | G | G | 10000 | 10000 | 0 |  |  | 0% | -100% | G |  | Project has been signed off and passed stage gate 5 to be removed by AW | G | [9 empty] | Current Forecast Spend £10000 | Stage Gate 5
[56 empty] | 100000 | 100000 | #N/A |  |  | 0% | #N/A | #N/A | This does not work | This is a test hope | #N/A | [9 empty] | Current Forecast Spend £100000 | Stage Gate 1
Formulas:
Rag Status = IF(AND([Actual Board Date]="",[Forcast Board Date]=""),"",IF(AND([Actual Board Date]="",[Forcast Board Date]<TODAY()),"R","G"))
Stage Gate 5 Completion = IF([Contractual Practical Completion]="","",DATE(YEAR([Contractual Practical Completion]),MONTH([Contractual Practical Completion])+3,DAY([Contractual Practical Completion])))
Forcast Board Date = IF([Stage Gate 1]="","",DATE(YEAR([Stage Gate 1]),MONTH([Stage Gate 1])+1,DAY([Stage Gate 1])))
Note on D2: veronicasenior: Choose from drop down menu
Note on E2: veronicasenior: Choose from drop down menu
Note on G2: veronicasenior: Insert from drop down menu

## Change Control Register
Change Control Register - Property Care Programme
Project ID | Project Details | Change Request Description | Summary of Impact (Cost / Schedule / Quality ) | Reason for Change | Submitted By | Date Submitted | Date Approved / Rejected | Approval / Rejection comment
PCP/12/033 | Albany House - Plant Optimisation | Professional Cleaning of Air Systems | cost impact £ 135,676 | Increase efficiency of the building | Jerry Young | 2015-01-07 | 2015-01-21 | Chairman's action
PCP/12/033 | Albany House - Plant Optimisation | Budget amendment | £ 59,576 cost increase (new Budget confirmed £ 225,717) | Water Systems Commissioning in accordance with Core Groups recommendations to enhance the optimisation of Mech Systems. Works will be carried for 8 weeks (Finish date change from 27/11/2015 to 19/02/2016) | Jerry Young | 2015-11-20 | 2015-11-24 | Approved
PCP/12/033 | Albany House - Plant Optimisation | Budget amendment | 6 weeks on programme (new project finish date 1/04/2016) £ 25,000 cost increase (New Budget confirmed £ 250,717) | Air Systems remedial works in accordance with Core Group recommendations to achieve the TfL criteria | Jerry Young | 2016-02-01 | 2016-02-04 | Approved
PCP/12/033 | Albany House - Plant Optimisation | Programme Extension | 11 weeks on programme (new project finish date 12/08/2016) | Rebalancing and commissioning of the Air System together with the witnessing and commissioning of the wet systems. The work is a direct result of Core Group refusal to work with TfL | Jerry Young | 2016-06-21 | 2016-06-22 | Approved
PCP/12/033 | Albany House - Plant Optimisation | Programme Extension/ Budget amendment | 2 weeks on programme (new project finish date 31/08/2016) £ 16,790 cost increase (New Budget confirmed £ 267,507) | Undertake detailed condition report on mechanical and BMS functionality | Jerry Young | 2016-06-21 | 2016-06-22 | Approved
PCP/12/033 | Albany House - Plant Optimisation | Budget amendment | £ 33,268 cost increase (New Budget confirmed £ 300,775) | Undertake the replacement of critical faulty valves with new fixed Qrifice double regulating valves in various location | Jerry Young | 2016-06-21 | 2016-06-22 | Approved
PCP/12/039 | Multisite - Install BMS to Critical IT Facilities | Change of Contractor | Cost impact - negligible programme impact being assessed | overcome poor performance issues with Mitie Controls | Jerry Young | 2014-06-05
PCP/12/039 | Multisite - Install BMS to Critical IT Facilities | Impact of technical / operational issues on cost and programme | being assessed |  | Jerry Young | 2014-12-04
PCP/13/010 | Oxford Circus House BMS connectivity / standards upgrade | Programme revision to reflect full range of activities / Actual start date / FAC OPPS Close out | 8 wks on programme | based on contractor programme | John Murphy | 2014-03-13 | 2014-04-14 | Approved
PCP/13/010 | Oxford Circus House BMS connectivity / standards upgrade | Additional Works | Cost / schedule impact being assessed | Additional works requested by Fac Ops | John Murphy | 2014-11-26
PCP/13/010 | Oxford Circus House BMS connectivity / standards upgrade | Increase of delivery scope to provide Building Services enhancements | 20 weeks on programme (new baseline finish date 29/12/2015) | Add. works will provide broader connectivity across BMS network, greater consistency in the system. Also, will improve system functionality, control and operation | John Murphy | 2015-08-13 | 2015-08-13 | Approved
PCP/13/010 | Oxford Circus House BMS connectivity / standards upgrade | Extension on Programme | 31 days on programme (new baseline finish date 30/01/2016) | Delay by Air Handling Unit manufacturer in attending site to inspect AHU resulted the change in completion date | John Murphy | 2015-11-11 | 2015-12-07 | Approved
PCP/13/014 | 13 Allsop Pl - Versatemp refurbishment & R22 Replacement | Programme Extension/ Budget amendment | Critical Delivery Date 12 Nov 2015 £ 3,578 cost increase (new Budget confirmed £ 275,578) | Extra Works - Repair and Upgrade All Electrical Spares to Versatemp Units | Jerry Young | 2015-11-11 | 2015-11-17 | Approved
PCP/14/007 | Multisite - Fire Compartmentation Work | Programme Extension | 3 months on programme (new baseline finish date 25/08/2015) | Change request submitted to align the Baseline Completion date with Practical Completion date | John Murphy | 2016-01-14 | 2016-01-20 | Approved
PCP/14/007 | Multisite - Fire Compartmentation Work | Budget amendment | £ 6,250 cost increase (New Budget confirmed £ 564,250) | Additional Survey of Incomplete works needed | John Murphy | 2016-03-16 | 2016-03-23 | Approved
PCP/15/003 | Victoria Station House-Fire Doors | Budget amendment | £ 4,918 cost increase (New Budget confirmed £ 114,918) | Additional 5 doors to be renewed (riser cupboards) | John Cousins | 2016-04-18 | 2016-04-27 | Approved
PCP/15/006 | Baker Street Complex - Fire Compliance - Fire Alarms no MICC | Compliance works and schedule of recommendations as requested by Arup and TfL Team | cost impact £ 47,631 | to ensure project undertaken in compliance with the Brief, Fire Strategy and Fire Risk Assessment | Jerry Young | 2015-06-03 | 2015-06-24 | Approved
PCP/15/006 | Baker Street Complex - Fire Compliance - Fire Alarms no MICC | Programme Extension | Impact on programme (baseline extended); Impact on cost assessed in CCR 2015/1 | Decision to undertake the Asbestos Impact Assessments and Detailed Design Development | Jerry Young | 2015-06-03 | 2015-06-24 | Approved
PCP/15/006 | Baker Street Complex - Fire Compliance - Fire Alarms no MICC | Due to presence of Asbestos which compromise the installation of Fire Alarm installation remediation and fabric remedial works are required | Cost Impact £ 350,650 (New Budget confirmed - £ 1,506,239) | Works are required to ensure there are no contraventions to the Statutory Regulations and Compliance with Health and Safety Risk | Jerry Young | 2015-10-16 | 2015-10-16 | Approved
PCP/15/006 | Baker Street Complex - Fire Compliance - Fire Alarms no MICC | Programme Extension | 20 weeks on programme (new project finish date 30/09/2016) | Programme Extension due to presence of asbestos, remediation works, slow containment installation and poor contractor performance | Jerry Young | 2016-02-26 | 2016-03-16 | Approved
PCP/15/006 | Baker Street Complex - Fire Compliance - Fire Alarms no MICC | Budget amendment | Change to budget will be incorporated in to the Project Risk Costs | Due to the age and the existing ceiling it is now beyond economical repair to maintain. Ceiling soft fit is required to ensure fire compartment integrity | Jerry Young | 2016-08-19 | 2016-08-31 | Approved
PCP/15/007 | 172 BPR & Windsor House - Chillers Remedial | Programme Extension/ Budget amendment | 42 days on programme (new project finish date 11/03/2016) £ 122,100 cost increase (new Budget confirmed £ 423,300) | Extra Works discovered during intrusive site surveys and testing; Change of contract | John Cousins | 2015-10-30 | 2015-10-30 | Approved
PCP/15/009 | Palestra-Basement Leak Detection and Sump Pump | Budget amendment | £ 5,343 cost increase (New Budget confirmed £ 131,343) | Investigation and Report to perform by Gemimi Fire Ltd on Leak Detection System on Upper Floors, Palestra | John Cousins | 2016-06-16 | 2016-06-22 | Approved
PCP/15/009 | Palestra-Basement Leak Detection and Sump Pump | Programme Extension | Change to Project Completion date | Original scope of project did not incorporate installing the upgrade to the BMS. | John Cousins | 2016-08-12 | 2016-08-17 | Approved
PCP/15/009 | Palestra-Basement Leak Detection and Sump Pump | Programme Extension | Change of Proposed Project Start date to match actual start date |  | John Cousins | 2016-08-22 | 2016-08-31 | Approved
PCP/15/009 | Palestra-Basement Leak Detection and Sump Pump | Programme Extension | Change of Proposed Project Completion Date to 28/10/2016 | Allow more Time to Resolve BMS Issues | John Cousins | 2016-09-23 | 2016-09-28 | Approved
PCP/15/009 | Palestra-Basement Leak Detection and Sump Pump | Programme Extension | Change of Proposed Project Completion Date to 16/12/2016 | The Extension to the BMS system cannot be commissioned or tested because the existing system doesn't not operate as expected | John Cousins | 2016-10-21 | 2016-10-26 | Approved
PCP/15/011 | Old Broad Street - Install New HVAC System - Feasibility | Uplift in Budget for Passive Haus Consultant | £ 11,000 cost increase (New Budget confirmed £ 25,300) | Additional £ 11k required to undertake Passive Haus Feasibility and review in Old Broad Street | Karl Mitchell | 2015-11-20 | 2015-12-07 | Approved
PCP/15/011 | Old Broad Street - Install New HVAC System - Feasibility | Programme Extension/ Budget amendment | 2 weeks on programme (new project finish date 12/02/2016) £ 750 cost increase (New Budget confirmed £ 26,050) | Air Pressure Testing - Additional Building test to receive more accurate information for undertaking the modelling | Karl Mitchell | 2016-01-21 | 2016-01-21 | Approved
PCP/15/014 | Victoria Station House - Redecoration Works | Programme Extension and Budget increase to facilitate daylight dimming | 8 weeks on programme (new project finish date 26/10/2015) Cost impact - £ 20,000 (New Budget confirmed - £ 115,000) | Submitted design did not meet TfL Standards and did not offer daylight dimming. The subsequent design revision resulted delay and increase of the costs. | John Murphy | 2015-08-26 | 2015-09-07 | Approved
PCP/16/016 | Templar House - Boiler Replacement | Programme Extension/Budget Amendment | Change of Proposed Project Completion Date 12/12/2016 and £9311 Cost Increase to £179311 | Delay in delivery of the BMS Element of the project against the project schedule there is a need to extend the delivery period | John Murphy | 2016-09-07 | 2016-09-14 | Approved
PCP/16/016 | Templar House - Boiler Replacement | Budget amendment | £800 Cost increase to £180111 | Asbestos found and needs to be removed | John Murphy | 2016-10-19 | 2016-10-26 | Approved
PCP/16/017 | Palestra-Power Integration Project | Programme Extension | 16 weeks on programme (new project finish date 18/05/2016) | First test cancelled by TfL for business reasons which resulted the delay, additional time being required for re-evaluation of works stages and planning of target dates | Andrew Jefferies | 2016-03-09 | 2016-03-16 | Approved
PCP/16/019 | 172 BPR LV Infrastructure Upgrade | Programme Extension | Project Completion Date from 15/05/2016 to 23/12/2016 | Extension of time to programme due to illness of designer and design review has flagged further issue and design developemtn relating to acess and physical implications of undertaking work. Design due for completion by Christmas 2016 | Laurie Morely | 2016-11-04 | 2016-11-09 | Approved
Rech/15/ACR/10787 | LSTOC Accommodation Workstream | Programme Extension | Project Completion Date from 28/09/2016 to 09/11/2018 | Technical Fit-out delayed untill April 16 user acceptance was not completed until 01/09/2016 due to technical issues with new tunnels control system. Many other issue please refure to change Request | Tony Hunter | 2016-11-04 | 2016-11-09 | Approved
Rech/15/ACR7705 | Griffith House - Replacement 2 Roller Shutter Doors | Programme Extension/ Budget amendment | 2 weeks on programme (new baseline finish date 31/08/2015) Budget Correction of £10,317 (New Budget confirmed - £ 58,744) | Initial Budget Incorrectly Recorded/ Extension of Time to Complete the Defects Resolution | John Murphy | 2015-07-31 | 2015-08-10 | Approved
RECH/16/ACR/13748 | 13 Allsop Place Refurbishment ex-police cells to make new into lockers | Programme Extension | Project Completion Date from 28/09/2016 to 09/11/2017 | Extenstion of time to programme due to late receipt of design information | Laurie Morely | 2016-11-04 | 2016-11-09 | Approved
RECH/16/ACR12908 | Griffith House 3rd Floor Industrial Kitchen | Programme Extension | Project Completion Date 15/11/2016 | Snagging deal Leg to be Removed | Martina Perkins | 2016-10-21 | 2016-10-26 | Approved
Rech/16/ACR14011 | Palestra 2nd Floor Kitchen | Programme Extension/ Budget amendment | Change to Baseline Start date from 23/07/2016 to 09/01/2017 Change to Baseline Completion from 12/08/2016 to 13/02/2017 Increase to budget from £40000-£42000 | Progress to Project Delivery | Martina Perkins | 2016-11-18 | 2016-11-23 | Approved
RECH/16/ACR646 | Palestra 9th Floor Meeting Rooms | Programme Extension/Budget Amendment | £25600 Cost increase New Project Finish Date 07/12/2016 |  | Martina Perkins | 2016-10-21 | 2016-10-26 | Approved
Rech/16/ACR7149 | RNC Relocation to Palestra | Programme Extension/ Budget amendment | 4 weeks on programme (new project finish date 05/10/2015) £ 59,000 cost increase (new EFC £ 112,500) | Change/Extended of work scope of RNC Relocation | Martin Smith | 2015-08-04 | 2015-08-06 | Approved
Rech/16/ACR7149 | RNC Relocation to Palestra | Programme Extension/ Budget amendment | 23 weeks on programme (new project finish date 14/03/2016) £ 40,000 cost increase (new EFC £ 152,500) - ( £40k covered by PCP budget) | Extended Scope of Project to incorporate works to adapt Solar Shading Devices, 4th and 5th Fl 55 Broadway | Martin Smith | 2015-10-22 | 2015-10-28 | Approved
Rech/16/ACR7149 | RNC Relocation to Palestra | Programme Extension | 27 weeks on programme (new baseline finish date 11/04/2016) | Extended Scope of Project to incorporate works to adapt Solar Shading Devices, 4th and 5th Fl 55 Broadway | Martin Smith | 2016-01-04 | 2016-01-06 | Approved
Rech/16/ACR7149 | Facilitating Construction Works for RNC Relocation to Palestra | Programme Extension | 4 weeks on programme (new project finish date 09/05/2016) | Extend Project Close to accommodate supplier delay in planning and manufacture of blinds impacting on works on site | Martin Smith | 2016-03-11 | 2016-03-16 | Approved
Rech/16/ACR7149 | Facilitating Construction Works for RNC Relocation to Palestra | Programme Extension | 4 weeks on programme (new project finish date 06/06/2016) | Extend Project Close to accommodate supplier delays in planning and manufacture of blinds impacting on works on site & close out | Martin Smith | 2016-04-21 | 2016-11-09 | Approved
Note on C2: Describe the change being requested including analysis of impact.
Note on D2: EdwardClancy: Quantify the Impact of the change
Note on F2: Identify the person submitting the change request.
Note on G2: Enter the date the change request was submitted.
Note on I2: Use this field to provide running commentary with regards approval. Prefix with Date and Initials of author e.g. '12/08/04; DM - Approval given'

## Finance (hidden)
|  | Project Details |  |  |  | In Year Position as @ P9
Project ID | WBS Element | Project Name | Project Stage | Building | PM | Costs Incurred | To Occur | Total
Commercial | RX04F.033.109.05 | Procurement Support | 0 | Multisite | VS | 46301 | 0 | 46301
Project Management | RX04F.014.2007.709.04 | Project Management | 0 | Multisite | VS | 19460 | 7425 | 26885
Health & Safety | RX04F.033.309.01 | Health & Safety | 0 | Multisite | VS | 21620 | 0 | 21620
PCP/12/033 | RX04F.014.2007.708.02 | Albany House - Plant Optimisation | 5 - Delivery | Albany House | JY | 53779 | 45540 | 99319
PCP/14/007 | RX04F.033.207.03 | Multisite - Fire compartmentation work | 6 - Project Close | Multisite | JM | 6250 | 0 | 6250
PCP/15/003 | RX04F.014.2007.903.01 | Victoria Station House-Fire Doors | 5 - Delivery | Victoria Station House | JC | 102415 | 0 | 102415
PCP/15/006 | RX04F.014.2007.903.03 | Baker Street Complex-Fire Alarm Phase 2 | 5 - Delivery | Baker Street | JY | 379574 | 218815 | 598389
PCP/15/007 | RX04F.033.201.05 | Windsor House Chiller Remedials | 4 - Detailed Design | Windsor House/172 BPR | JC | 168974 | 695719 | 864693
PCP/15/009 | RX04F.033.201.07 | Basement Leak Detection and Sump Pump | 4 - Detailed Design | Palestra | JC | 96973 | 1114 | 98087
PCP/15/014 | RX04F.014.2007.903.04 | Victoria Station House - Redecoration | 6 - Project Close | Victoria Station House | JM | 0 | 0 | 0
PCP/16/006 | RX04F.033.303.04 | Toilet Flushing Upgrade | 4 - Detailed Design | Palestra | JC | 18935 | 500 | 19435
PCP/16/007 | RX04F.033.303.02 | 200 BPR Toilet Refurbishment | 3 - Concept Design | 200 BPR | HH | 17500 | 0 | 17500
PCP/16/010 | RX04F.033.303.03 | Griffith House Redecs | 4 - Detailed Design | Griffith House | HH | 0 | 0 | 0
PCP/16/016 | RX04F.033.301.01 | Templar House - Boiler Replacement | 5 - Delivery | Templar House | JM | 124370 | 12191 | 136561
PCP/16/018 | RX04F.033.303.08 | VSH Roof and Facade Repair | 3 - Concept Design | Victoria Station House | JC | 7451 | 23400 | 30851
PCP/16/019 | RX04F.033.302.06 | 172 BPR LV Infrastructure Upgrade | 4 - Detailed Design | 172 BPR | LM | 50529 | 8285 | 58814
PCP/16/020 | RX04F.033.307.01 | Building Facade Risk Assessment | 2 - Feasibility | Multisite | JM | 7500 | 0 | 7500
FacOps/16/001 | RX04F.033.302.02 | 172 BPR 5th Floor Power | 4 - Detailed Design | 172 BPR | JM | 126281 | 42766 | 169046
PCP/16/022 | RX04F.033.305.02 | Penton Street Upper Roof | 4 - Detailed Design | Penton Street | HH | 131096 | 8904 | 140000
PCP/16/023 | RX04F.033.307.03 | PA/VA | 3 - Concept Design | Broadway | HH | 0 | 0 | 0
PCP/16/024 | RX04F.033.307.04.02 | Griffiths House Facade Repairs - Project | 1 - Outline Definition | Griffith House | JC | 0 | 0 | 0
PCP/16/024 | RX04F.033.307.04.01 | Griffiths House Facade Repairs - Enabling | 1 - Outline Definition | Griffith House | JC | 0 | 0 | 0
Rech/16/ACR14011 | RX04F.033.303.10 | 2nd Floor Kitchen | 5- Delivery | Palestra | MP | 0 | 0 | 0
PCP/16/017 | RX04F.033.302.01 | Palestra-Power Resilience | 5 - Delivery | Palestra | AJ | 47466 | 3000 | 50466
Rech/14/ACR3958 | IO 1012369 | New Consulting Rooms | Closed | Townsend House | HH |  |  | 10915.6
Rech/15/ACR10556-10722 | IO 2146842 | 17th Floor Partition | Delivery | Windsor House | MS |  |  | 5250
Rech/15/ACR10787 | RX04F.036.005 | LSTOC Accommodation Workstream | Delivery | Palestra & 200BPR | TH |  |  | 77471.82
Rech/16/ACR10994 | IO 2147043 | Templar House Basement | Delivery | Templar House | MS |  |  | 0
Rech/16/ACR7149 | RX04F.036.002 RX04F.033.303.09 | RNC Relocation works to Palestra | Delivery | Palestra / 55 Broadway | MS |  |  | 1304
Rech/16/ACR11245 | CC 11000 | Templar House Tea points | Delivery | Templar House | AC |  |  | 4950
Rech/16/ACR12721 | CC 10284 | 200 BPR New Kitchens 4th 5th 6th Floor | Delivery | 200 BPR | AC |  |  | 82000
Rech/16/ACR11193 | IO 2147303 | Albany House Ground Floor Kitchen Refurbishment | Delivery | Albany House | MP |  |  | 25825.53
Rech/16/ACR12908 | IO 2147405 | Industrial Kitchen/Rest Room Refurbishment | Delivery | Griffiths House | MP |  |  | 26302.86
Rech/16/ACR14719 | IO 2147503 | 9th Floor Kitchen Refurb | Delivery | Albany House | MP |  |  | 20898.3
Rech/16/ACR12770 | IO 2130087 | Locker Rooms | Delivery | Cranbourne Street | MP |  |  | 20885.62
Rech/16/ACR6446 | IO 2146942 | New Meeting Rooms for Steve Burton | Delivery | Palestra | MP |  |  | 74456.34
Rech/16/ACR14308 | IO 2147484 | Auditorium, 2nd Floor | Delivery | Pier Walk | MP |  |  | 61008.55
Rech/16/ACR13748 | IO 2147462 | Ex Police Cells refurbishment | Delivery | 13 Allsop Place | LM |  |  | 107303.86
OCR/16/001 | RX04F.029.037 | Uniform store relocation to Penton St | Delivery | Penton Street | LM |  |  | 1120408.71
Rech/16/ACR13713 | CC10284 | 17th Floor | Delivery | Windsor House | MP |  |  | 5555
Rech/16/ACR14011 | IO 2130220 | 2nd Floor Kitchen | Delivery | Palestra | MP |  |  | 0

## Rag Coding (hidden)
AGGG | G | YES | YES | YES | 2017-02-02 | 0
GAGG | G | NO | N/A | On Hold | 2017-02-02 | 1
GGAG | G |  | NO | NO
GGGA | G
AAGG | G
AGAG | G
AGGA | G
GAGA | G
GAAG | G
GGAA | G
AAAG | A
AAGA | A
AGAA | A
GAAA | A
AAAA | A
GGGG | G
G | G
GG | G
GGG | G
A | A
AA | A
AAA | A
GA | G
AG | G
GAA | A
GGA | G
AGG | G
AAG | A
AGA | A

## Sheet2 (hidden)
Select Project: | Project 1

## Head Office Buildings (hidden)
172 Buckingham Palace Road | 172 Buckingham Palace Road
200 Buckingham Palace Road | 200 Buckingham Palace Road
Albany House | Albany House
Aldgate Station (EC3N) | Aldgate Station, EC3N 1AH
Allsop Place, 13 (NW1) | 13 Allsop Place. NW1 5LJ
Allsop Place, 15-17 (NW1) | 15-17Allsop Place, NW1 5LJ
Ashfield House (W14) | 7 Beaumont Avenue, W14 9UY
Baker Street Revenue Control (NW1) | 210/212 Baker Street, NW1 5RT
Baker Street, 210-212 (NW1) | 210/212 Baker Street, NW1 5RT
Baker Street, 216 (NW1) | 216 Baker Street, NW1 5RT
Blackwall (E14) | 19 Naval Row, Poplar, E14 9RY
Borough High Street, 31 (SE1) | 31 Borough High Street, SE1 9AW
Chancel Street Garage Complex (SE1) | 8 Chancel Street, SE1 0UX
Davies Street, 75 (W1) | 75 Davies Street, Westminster, W1K 5JN
Griffith House (NW1) | 280 Marylebone Road, NW1 5RJ
Lost Property Office (NW1) | 200 Baker Street, NW1 5RZ
Multi Sites | Multi Sites
Old Broad Street (EC2) | 70 Old Broad Street, EC2M 1QT
Oxford Circus House (W1) | 245 Oxford Street, W1D 2LS
Palestra | Palestra
Pelham Street (SW7) | 63-81 Pelham Street, SW7 2NJ
Penton Street (NW1) | 15 Penton Street, N1 9PU
Pier Walk | Pier Walk
Premier House (W9) | 313 Kilburn Lane, W9 3EG
Selbie House (NW1) | 13 Allsop Place, NW1 5LJ
Templar House | Templar House
Townsend House | Townsend House
Townsend House (SW1) | Greycoat Place, SW1P 1BL
Uniform Store (W3) | Unit 2, Victoria Industrial Estate,
Vandon St Garage (SW1) | Vandon Street, SW1
Victoria Station House | Victoria Station House
Western House (W1) | 237-239 Oxford Street, W1R 1AB
Windsor House Complex | 42-50 Victoria Street SW1H 0TL
Broadway Complex | 55 Broadway SW1H 0BD

## Sponsors (hidden)
Paul Doyle
Esther Sharples
Simona Kuhl
Nicky Mahood
Christine Peppiatt
Veronica Senior
Amanda Morrison

## Project Managers & FacOps Reps (hidden)
John Murphy | Robert Sciberras
John Cousins | Hakeem Makanju
Helena Healy | Dave Parr
Martina Perkins | Quinten Babcock
Andrew Jefferies | Mike O'Connor
Alan Crossan
Tony Hunter
Martin Smith
Laurie Morely
Jerry Young

## Resources Data
Project ID | Project Managers | Column1 | Project Description | Pulled Project Manager | Start date | PulledCompletion | Completion | Days | Today | Pulled DaysColumn1 | Pulled DaysColumn2
PCP/16/023 | Helena Healy | Broadway PA/VA system.... | Broadway PA/VA system | Helena Healy | 2016-11-15 | 2017-04-04 | 2017-04-04 | 140 | 2016-12-15 | 140 | Stage Gate 5
PCP/15/007 | John Cousins | 172 BPR & Windsor House Chiller Remedial.... | 172 BPR & Windsor House Chiller Remedial | John Cousins | 2014-01-06 | 2017-03-20 | 2017-03-20 | 1169 | 2016-12-15 | 1169 | Stage Gate 5
PCP/15/009 |  | Basement Leak Detection and Sump Pump.... | Basement Leak Detection and Sump Pump | John Cousins | 2015-09-15 | 2016-12-16 | 2016-12-16 | 458 | 2016-12-15 | 458 | Stage Gate 5
PCP/16/006 |  | Toilet Flushing Upgrade.... | Toilet Flushing Upgrade | John Cousins | 2015-09-15 | 2016-08-10 | 2016-08-10 | 330 | 2016-12-15 | 330 | Stage Gate 4
PCP/16/018 |  | VSH Roof and Facades Repairs.... | VSH Roof and Facades Repairs | John Cousins | 2015-09-22 | 2017-05-15 | 2017-05-15 | 601 | 2016-12-15 | 601 | Stage Gate 4
PCP/16/024 |  | Griffith House Facade Repairs.... | Griffith House Facade Repairs | John Cousins | 2016-11-15 |  |  | #VALUE! | 2016-12-15 | #VALUE! | Stage Gate 1
PCP/16/020 | John Murphy | Building Facades Risk Assessments (7 Building).... | Building Facades Risk Assessments (7 Building) | John Murphy | 2016-07-20 | 2017-06-22 | 2017-06-22 | 337 | 2016-12-15 | 337 | Stage Gate 4
PCP/16/007 |  | 200 BPR Toilet Refurbishment.... | 200 BPR Toilet Refurbishment | John Murphy | 2015-10-28 | 2016-10-07 | 2016-10-07 | 345 | 2016-12-15 | 345 | Stage Gate 2
PCP/16/016 |  | Templar House Boiler Replacement.... | Templar House Boiler Replacement | John Murphy | 2015-07-14 | 2016-12-12 | 2016-12-12 | 517 | 2016-12-15 | 517 | Stage Gate 5
FACOPS/16/001 |  | 172 BPR 5th Floor Power.... | 172 BPR 5th Floor Power | John Murphy | 2016-07-20 | 2016-12-01 | 2016-12-01 | 134 | 2016-12-15 | 134 | Stage Gate 5
Rech/16/ACR6446 | Martina Perkins | New Meeting Rooms for Steve Burton EOS Director .... | New Meeting Rooms for Steve Burton EOS Director | Martina Perkins | 2016-04-18 | 2016-12-07 | 2016-12-07 | 233 | 2016-12-15 | 233 | Stage Gate 5
RECH/16/ACR16145 |  | Bringing Back to use Staircase/chained door leading to.... | Bringing Back to use Staircase/chained door leading to the track | Martina Perkins | 2016-11-15 | 2017-04-03 | 2017-04-03 | 139 | 2016-12-15 | 139 | Stage Gate 5
Rech/16/ACR14011 |  | 2nd Floor Kitchen area Palestra.... | 2nd Floor Kitchen area Palestra | Martina Perkins | 2016-07-25 | 2017-02-13 | 2017-02-13 | 203 | 2016-12-15 | 203 | Stage Gate 5
PCP/12/033 | Outside Consultant | Albany House - Plant Optimisation.... | Albany House - Plant Optimisation | Jerry Young | 2012-01-30 | 2017-02-17 | 2017-02-17 | 1845 | 2016-12-15 | 1845 | Stage Gate 5
PCP/15/006 |  | Baker Street Complex - Fire Compliance - Fire Alarms n.... | Baker Street Complex - Fire Compliance - Fire Alarms no MICC | Jerry Young | 2012-10-01 | 2017-04-30 | 2017-04-30 | 1672 | 2016-12-15 | 1672 | Stage Gate 5
PCP/16/019 |  | 172 BPR LV Infrastructure Upgrade.... | 172 BPR LV Infrastructure Upgrade | Laurie Morely | 2015-12-17 | 2016-12-23 | 2016-12-23 | 372 | 2016-12-15 | 372 | Stage Gate 4
Rech/16/ACR12721 |  | 200 BPR New Kitchens 4th,5th and 6th Floors.... | 200 BPR New Kitchens 4th,5th and 6th Floors | Alan Crossan | 2016-01-29 | 2016-12-05 | 2016-12-05 | 311 | 2016-12-15 | 311 | Stage Gate 5
RECH/16/ACR13748 |  | 13 Allsop Place Refurbishment ex-police cells to make .... | 13 Allsop Place Refurbishment ex-police cells to make new into lockers | Laurie Morely | 2016-07-18 | 2016-11-18 | 2016-11-18 | 123 | 2016-12-15 | 123 | Stage Gate 5
OCR/16/001 |  | Uniform Store relocation to Penton Street.... | Uniform Store relocation to Penton Street | Laurie Morely | 2016-08-29 | 2016-12-23 | 2016-12-23 | 116 | 2016-12-15 | 116 | Stage Gate 5
Rech/15/ACR10787 |  | LSTOC Accommodation Workstream.... | LSTOC Accommodation Workstream | Tony Hunter | 2015-01-01 | 2016-11-23 | 2016-11-23 | 692 | 2016-12-15 | 692 | Stage Gate 5
Rech/16/ACR10994 |  | Templar House Basement Changeing Room for Chancery Lan.... | Templar House Basement Changeing Room for Chancery Lane Escalator Replacement Project | Martin Smith | 2016-01-01 | 2016-02-15 | 2016-02-15 | 45 | 2016-12-15 | 45 | Stage Gate 5
Formulas:
Completion = IF([PulledCompletion]=0/1/1900,"",[PulledCompletion])

## Resources Planner
11